## Sprint Summary
CVP Monitri Website - Sprint Plan
Prepared by NOCPL Updated Date: 22nd March 2021
| SPRINT NO. | START DATE | END DATE | Sprint Goal
30 | SPRINT #1 | 2021-03-29 | 2021-04-09 | Mentioned in Delivery plan
30 | SPRINT #2 | 2021-04-12 | 2021-04-23 | Mentioned in Delivery plan
30 | SPRINT #3 | 2021-04-26 | 2021-05-07 | Mentioned in Delivery plan
10 | SPRINT #4 | 2021-05-10 | 2021-05-21

## Delivery Plan
CVP Monitri Website - Developmet Plan & Delivery Schedule
Prepared by Weblineindia, Updated Dated: 22nd March 2021
TASK GROUP | TASK DETAILS | NOTES
SPRINT {#1} : FROM {30th March 2021} TO {09th April 2021}
Web Development | Web Application Layout Development
Login, Forgot Password, Reset Password & Home page design
Group, Members Page, Members House & Members House checkup page design
Setup Web Application with Angular
Setup Database and anlyze database structures
Setup ADA compliance with HTML & Angular developed code
Staging Deployment | Staging Deployment | Staging deployment for completed changes for beta review
Login page with Backend API development
Forgot Password, Reset Password with Backend API development
Home page with Backend API development
Validations & Email (Forgot & Reset Password) setup
Unit testing
Staging Deployment | Staging Deployment 1st Demo | Staging deployment for completed changes for beta review
SPRINT {#2} : FROM {12th April 2021} TO {23rd April 2021}
Web Development | Sprint - 2 Features Discussion
Home page Filters development
Home page CPV Summary
Search functionality development
Unit testing
Staging Deployment | Staging Deployment | Staging deployment for completed changes for beta review
Group Page with backend API development
Group Summary page with backend API development
Validation setup
Unit testing
QA for completed functionalities
Staging Deployment | Staging Deployment 2nd Demo | Staging deployment for completed changes for beta review
SPRINT {#3} : FROM {26th April 2021} TO {07th May 2021}
Web Development | Sprint - 3 Features Discussion
Members screen with backend API development
Members House page with backend API development
Members House checking page with backend API development
Validation setup
Unit testing
QA for completed functionalities
Staging Deployment | Staging Deployment | Staging deployment for completed changes for beta review
Chat Board & Tele-Calling integration
Resolve QA points
Unit testing
QA for completed functionalities
Staging Deployment | Staging Deployment 3rd Demo | Staging deployment for completed changes for beta review
SPRINT {#4} : FROM {10th May 2021} TO {21st May 2021}
Web Development | Sprint – 4 Features Discussion
Dashboard Integration
Reports development
QA for completed functionalities
Resolve QA points
Staging Deployment | Staging Deployment 4th Demo | Staging deployment for completed changes for beta review
QA for Complete application
Mobile App | API development for Mobile application
Resolve QA points
Website Deployment on Live server

## Acceptance Criteria
|  | 1 |  |  | 2 |  |  | 3
User story : | As a user, I want to enter my credentials,so that I will be able to access my account |  | User story : | As a user, I want to be able to recover the password to my account ,so that I will be able to access my account in case I forgot the password |  | User story : | As a user, I want to be able to change the password,so that I will be able to access my account in case of password is expired or default one.
Scenario | Log In |  | Scenario | Forgot Password |  | Scenario | Change Password
Given | The user navigates to the log in page |  | Given | The User navigates to the log in page |  | Given | The User navigates to the change password link
When | The user enter invalid credentials |  | When | The user selects <Forgot Password> option and enters an user id |  | When | The user enters a new password
Then | The system restrict to access the site |  | Then | The system sends the link to change password |  | Then | The system should ask to enter atleast 1 alpha,1 numeric, 1 special case,1 upper case and 1 lower case character
Given | The user navigates to the log in page |  | Given | The user receives the link via the email |  | Given | The User navigates to the change password link
When | The user enter valid credentials |  | When | The user navigates through the link received in the email |  | When | The user enters a new password
Then | The system allow to access his/her account |  | Then | The system enables the user to set a new password |  | Then | Password size should be atleast 8 characters
[6 empty] | Given | The user already entered old ,new and confirm password
[6 empty] | When | The user clicked on button to Change Password
[6 empty] | Then | The system enables the user to set a new password
|  | 4 |  |  | 5 |  |  | 6
User story : | As a user,I want to see home page details,so that I can take necessary action. |  | User story : | As a user,I want to see schedule,so that I can take necessary action |  | User story : | As a user,I want to view group page,so that I can take necessary action
Scenario | Home Page |  | Scenario | Schedule Page |  | Scenario | Group Page
Given | The user navigates to the Home page |  | Given | The user navigates to the Schedule page |  | Given | The user navigates to the Group page
When | The user view "Now" section |  | When | The user view details |  | When | The user view group details
Then | The user can see all the group details which are going to start within 10 minutes |  | Then | The user can see entire schedule mapped to him |  | Then | All members should be displayed along with Member Name,pin, status,distance from branch ,House Image,google map etc.
Given | The user navigates to the Home page |  | Given | The user flter details |  | Given | The user navigates to the Group page
When | The user view "Later" section |  | When | The user click on filter options |  | When | The user click on member details
Then | The user can see all the group details which are forthcoming |  | Then | System should be able to filter data based on group,time etc |  | Then | The user navigates to the member page
Given | The user navigates to the dashboard portion |  |  |  |  | Given | The user navigates to the Group page
When | The user enter dates |  |  |  |  | When | The user click on Audio/Video/Chat options
Then | Dashboard depicts cpv count,approve,pending and rejection count,rejection rate,avg group size,avg cpv time taken etc |  |  |  |  | Then | The user navigates to the respective option and perform the task
7
User story : | As a user,I want to see customer details,so that I can take approve/reject a customer.
Scenario | Customer Page
Given | The user navigates to the customer page
When | The user view Photo,House Images,KYC details,Past loan history,asset and financial status, details.
Then | The user has to approve/reject customer based on pre defined criteria
Given | The user navigates to the customer page
When | The user click on Audio/Video/Chat options
Then | The user navigates to the respective option and perform the task
Given | The user navigates to the customer page
When | The user click on House Images
Then | The user can view and compare house Images with near by house Images(150 meters)