## Sheet1
CGRS - Developmet Plan & Delivery Schedule
Prepared by NOCPL Development, Updated Dated: 07/11/2020
TASK GROUP | TASK DETAILS | NOTES | Status
SPRINT {#1} : FROM {21-09-2020} TO {28-09-2020}
Web Development | Web Application Layout Development
Login, Forgot Password, Reset Password & Home page design
Raise Complaint Screen, View Complaint and Forward Complaint Screen
Setup Web Application with Angular
Setup Database and anlyze database structures
Staging Deployment | Staging Deployment
SPRINT {#2} : FROM {01-10-2020} TO {11-10-2020}
Web Development | Sprint - 2 Features Discussion
Login page with Backend API development
Forgot Password, Reset Password with Backend API development
Home page with Backend API development
Validations & Email (Forgot & Reset Password) setup
Unit testing
Staging Deployment | Staging Deployment
SPRINT {#3} : FROM {15-09-2020} TO {15-10-2020}
Web Development | Sprint - 3 Features Discussion
Home page Filters development
Home page Compliant Summary
Date Search functionality development
Unit testing
Staging Deployment | Staging Deployment
SPRINT {#4} : FROM {29-10-2020} TO {7-11-2020}
Web Development | Sprint - 4 Features Discussion
|  |  |  | 29 | 7
User Mapping with backend API development
Complaint Status page with backend API development
Validation setup
QA for completed functionalities
Resolve QA points
QA for completed functionalities
Staging Deployment | Website Deployment on Live server