## Sheet1
Checkmate Web - Developmet Plan & Delivery Schedule
Prepared by NOCPL Developer Updated Dated: 9 Augst 2021
TASK GROUP | TASK DETAILS | NOTES | Status
SPRINT {#1} : FROM {27nd May 2021} TO {28th May 2021}
Web Development | Web Application Structure Create
Discuss Project Structure
Discuss Database Structure
Staging Deployment | Staging Deployment
SPRINT {#2} : FROM {31 May 2021} TO {4 June 2021}
Web Development | Web Application Layout Create
Login Page Design
Forgot Password Design
Reset Pssword Design
Home Page Design
Zone Master Design
Staging Deployment | Staging Deployment
SPRINT {#3} : FROM {7 June 2021} TO {11 June 2021}
Web Development | Sprint - 2 Features Discussion
Login page with Backend API development
Forgot Password with Backend API development
Reset Password with Backend API development
Zone Master Api Binding
Unit Testing Login
Staging Deployment | Staging Deployment
SPRINT {#4} : FROM {14 June 2021} TO {18 June 2021}
Web Development | Unit Testing-Forgot Password
Unit Testing-Reset Password
Unit Testing-Home Page
Unit Testing-Zone Master
Attached Dashbord page in Portal
Staging Deployment | Staging Deployment
SPRINT {#5} : FROM {21 June 2021} TO {25 June 2021}
Web Development | Sprint - 2 Features Discussion
Design for Bank Master
Design for State Master
Design for Area Master
Design for User master
Design for Branch and Audit Type Master
Staging Deployment | Staging Deployment
SPRINT {#6} : FROM {28 June 2021} TO {2 July 2021}
Web Development | Sprint - 5 Features Discussion
Bank and Audit Type with Backend API development
Area with Backend API development
User with Backend API development
Branch with Backend API development
State with Backend API development
Staging Deployment | Staging Deployment
SPRINT {#7} : FROM {5 July 2021} TO {9 July 2021}
Web Development | Sprint - 6 Features Discussion
Unit Testing Bank and Audit Type Master
Unit testing User master
Unit Testing Branch Master
Unit Testing of Area and State master
Staging Deployment | Staging Deployment
SPRINT {#8} : FROM { 12 July 2021} TO {16 July 2021}
Web Development | Sprint – 7 Features Discussion
Create UI for Question page
Create ui for Schedule page
Create ui for Center Data
Create UI for Member Data
Create UI for Audit Manager Review Ui page
Staging Deployment | Staging Deployment
SPRINT {#9} : FROM {19 July 2021} TO {23 July 2021}
Web Development | Sprint – 7 Features Discussion
API binding for Question Page
API binding for Schedule Page
API binding for Center Page
API binding for Member Page
API binding for AM Review Page
Staging Deployment | Staging Deployment
SPRINT {#10} : FROM {26 July 2021} TO {30 July 2021}
Web Development | Sprint – 7 Features Discussion
Unit Testing for Question Page
Unit Testing for Schedule Page
Unit Testing for Center Page
Unit Testing for Member Page
Unit Testing for AM Review Page
Staging Deployment | Staging Deployment
SPRINT {#11} : FROM {2 Augst 2021} TO {6 Augst 2021}
Web Development | Sprint – 7 Features Discussion
Create UI for AH Review Page
Create UI FOR AH Branch Review Page
Api Binding for AH Review Page
Api Binding for AH Branch Review Page
Unit Testing
Staging Deployment | Staging Deployment
SPRINT {#12} : FROM {9 Augst 2021} TO {9 Augst 2021}
Web Development | Sprint – 7 Features Discussion
Testing
Staging Deployment | Staging Deployment