## Sheet1
Rent Application - Developmet Plan & Delivery Schedule
Prepared by NOCPL Developer Updated Dated: 9 Augst 2021
TASK GROUP | TASK DETAILS | NOTES | Status
SPRINT {#1} : FROM {29-01-2021} TO {05-02-2021}
Web Development | Web Application Structure Create
Discuss Project Structure
Discuss Database Structure
Staging Deployment | Staging Deployment
SPRINT {#2} : FROM {08-02-2021} TO {13-02-021}
Web Development | Web Application Layout Create
Login Page Design
Forgot Password Design
Home Page Design
Staging Deployment | Staging Deployment
SPRINT {#3} : FROM {15-02 2021} TO {20-02-2021}
Web Development | Sprint - 2 Features Discussion
Login page with Backend API development
Forgot Password with Backend API development
Unit Testing Login
Staging Deployment | Staging Deployment
SPRINT {#4} : FROM {22-02-2021} TO {25-02-2021}
Web Development | Unit Testing-Forgot Password
Unit Testing-Home Page
Attached Dashbord page in Portal
Staging Deployment | Staging Deployment
SPRINT {#5} : FROM {26-02-2021} TO {28-02-2021}
Web Development | Sprint - 2 Features Discussion
Design for Rent Master
Design for Rent Option
Design for Report
Design for Dashboard
Staging Deployment | Staging Deployment
SPRINT {#6} : FROM {01-03-2021} TO {04-03-2021}
Web Development | Sprint - 5 Features Discussion
Connect API with Rent Master
Connect API with Rent Option
Connect API with Report
Connect API with Dashboard
Staging Deployment | Staging Deployment
SPRINT {#7} : FROM {05-03-2021} TO {09-03-2021}
Web Development | Sprint - 6 Features Discussion
Unit Testing Rent Master
Unit testing Rent option
Unit Testing Dashboard
Staging Deployment | Website Deployment on Live server