## Test cases
Name of the Client |  | NOCPL
Test Scenario |  | DCB
Test Environment |  | RO sourcing App
Tested By |  | Vijayakumar
Start Date & Time |  | 2024-02-26
End Date & Time |  | 2024-02-29
Loans Module
Test Case No. | Test Case Type | Navigation | Test Case Description | Expected Result | Test values | Test Result (Actual result) | Status (Pass/Fail) | Screens (Hyperlink)
L0001 | Functional | NA | BM Home Screen | BM Home Screen//NEW GROUP CREATION 1. In Login screen click on Esign option 2. Click on Download option 3. Disbursement request completed centers will reflect in the Group list with member count |  | As expected | Pass
L0002 | Functional | NA | BM Home Screen | 1. Click on the center name, Member list will reflect 2. Click on the member name, member details will reflect to process Esign 3. Click on the eSign option |  | Iteration 1: Not expected Ekyc not fetching data properly. Iteration 2: As excepted | Pass
L0003 | Functional | NA | BM Home Screen | 1. AOF preview will be generated 2. Click proceed to move to eSign option screen 3. Select OTP or Biometric option for eSign 4. Confirm the name and mobile number reflecting in the screen, these should match with Ekyc details for eSign else eSign will be declined |  | Iteration 1: As expected Iteration 2: Not as excepted AOF is not being generated. Iteration3 : As expected | Pass
L0004 | Functional | NA | BM Home Screen | 1. After selecting the eSign option click proceed 2. Click the Tick box and click on sig document |  | Iteration 1: As expected Iteration 2: As excepted Iteration3: As expected Iteration4 : Not as expected selecting the eSign option and clicking proceed, the agree button is still accessible Iteration5: As expected | Pass
L0005 | Functional | NA | BM Home Screen | 1. NSDL E Gov screen will open for eSign process 2. Click OK on terms and conditions 3. Enter Aadhar number Virtual ID and tick on Terms and conditions option 4.Click on Capture figure print 5.Get member Thumb impression |  | Iteration 1: As expected Iteration 2: As excepted Iteration3: As expected Iteration4 : As excepted Iteration5: As Expected | Pass
L0006 | Functional | NA | BM Home Screen | 1. Once finger print captured click on OK 2. Document Signed screen will popup •3. Wait for the timer of 5 seconds to complete / update the eSign process |  | Iteration 1: As expected Iteration 2: As excepted Iteration3: As expected Iteration4 : As expected Iteration5: As Expected | Pass
L0007 | Functional | NA | BM Home Screen | 1. After member, nominee and Facilitator (BM) Esign completed Generate Group Agreement option will be enabled in the bottom of the screen 2. Follow Same process to eSign agreement 3.Have to eSign sequentially (1,2,3,4,,,) |  | Iteration 1: As expected Iteration 2: As excepted Iteration3: As expected Iteration4 : As expected Iteration5: Not as expected unable to generate the group agreement. Iteration6: As expected | Pass
L0008 | Functional | NA | BM Home Screen | 1. After completing agreement eSign in agreement open Group list 2. Click the Cloud upload option |  | Iteration 1: As expected Iteration 2: As excepted Iteration3: As expected Iteration4 : As expected Iteration5: As expected Iteration6: As expected | Pass

## Itteration No 1
Name of the Client |  | NOCPL
Test Scenario |  | DCB
Test Environment |  | RO sourcing App
Tested By |  | Vijayakumar
Start Date & Time |  | 2024-02-26
End Date & Time |  | 2024-02-26
Itteration No |  | 1
Test Case No. | Pass/Fail
L0001 | Pass
L0002 | Fail
L0003 | Pass
L0004 | Pass
L0005 | Pass
L0006 | Pass
L0007 | Pass
L0008 | Pass

## Itteration No 2
Name of the Client |  | NOCPL
Test Scenario |  | DCB
Test Environment |  | RO sourcing App
Tested By |  | Vijayakumar
Start Date & Time |  | 2024-02-26
End Date & Time |  | 2024-02-26
Itteration No |  | 2
Test Case No. | Pass/Fail
L0001 | Pass
L0002 | Pass
L0003 | Fail
L0004 | Pass
L0005 | Pass
L0006 | Pass
L0007 | Pass
L0008 | Pass

## Itteration No 3
Name of the Client |  | NOCPL
Test Scenario |  | DCB
Test Environment |  | RO sourcing App
Tested By |  | Vijayakumar
Start Date & Time |  | 2024-02-27
End Date & Time |  | 2024-02-27
Itteration No |  | 3
Test Case No. | Pass/Fail
L0001 | Pass
L0002 | Pass
L0003 | Pass
L0004 | Fail
L0005 | Pass
L0006 | Pass
L0007 | Pass
L0008 | Pass

## Itteration No 4
Name of the Client |  | NOCPL
Test Scenario |  | DCB
Test Environment |  | RO sourcing App
Tested By |  | Vijayakumar
Start Date & Time |  | 2024-02-27
End Date & Time |  | 2024-02-27
Itteration No |  | 4
Test Case No. | Pass/Fail
L0001 | Pass
L0002 | Pass
L0003 | Pass
L0004 | Pass
L0005 | Pass
L0006 | Pass
L0007 | Pass
L0008 | Pass

## Itteration No 5
Name of the Client |  | NOCPL
Test Scenario |  | DCB
Test Environment |  | RO sourcing App
Tested By |  | Vijayakumar
Start Date & Time |  | 2024-02-28
End Date & Time |  | 2024-02-28
Itteration No |  | 5
Test Case No. | Pass/Fail
L0001 | Pass
L0002 | Pass
L0003 | Pass
L0004 | Pass
L0005 | Pass
L0006 | Pass
L0007 | Fail
L0008 | Pass

## Itteration No 6
Name of the Client |  | NOCPL
Test Scenario |  | DCB
Test Environment |  | RO sourcing App
Tested By |  | Vijayakumar
Start Date & Time |  | 2024-02-28
End Date & Time |  | 2024-02-28
Itteration No |  | 6
Test Case No. | Pass/Fail
L0001 | Pass
L0002 | Pass
L0003 | Pass
L0004 | Pass
L0005 | Pass
L0006 | Pass
L0007 | Pass
L0008 | Pass